## Sheet1
AREA | Week 1 (2 April To 8 April)
| EQUIPMENT | Schedule PM | PM done
PV | PV INSPECTION - D | 7 | 5
PV | WEATHER MONITORING STATION - D | 7 | 5
PV | ACRS ROBOTS OPERATION - D | 7 | 4
PVSS | DAILY SUBSTATION INSPECTION - D | 7 | 5
PVSS | POWER TRANSFORMER DGA TEST - D | 7 | 5
PVSS | INDOOR HOUSEKEEPING - D | 7 | 5
PVSS | CCTV INSPECTION - D | 7 | 5
PVSS | WEATHER MONITORING STATION - W | 9 | 0
PVSS | SVG COOLING UNITS DUST CLEANING - W | 6 | 4
PVSS | EDG TEST RUN - SB-W | 1 | 0
PVSS | EDG TEST RUN - SS- W | 1 | 0
PV | POWER STATION MAINTENANCE - M | 33 | 0
PVSS | FIRE ALARM SYSTEM INSPECTION - M | 7 | 0
PVSS | TOOLS AND EQUIPMENTS INSPECTION - M | 1 | 0
PVSS | ALL FACILITIES LIGHTING AND POWER SYSTEM-M | 1 | 0
PVSS | POWER STATION MAINTENANCE - HY | 14 | 6
PV | ARCS ROBOTS MAINTENANCE - HY | 133 | 100
PV | SCB'S MAINTENANCE - HY | 14 | 6
PV | HVAC SYSTEM MAINTENANCE - M | 2 | 5
| TOTAL | 271 | 155
| COMPLIANCE SCORE | 57.2%
| PENDING | 42.8%
AREA | Week 2 (9 April To 15 April)
| EQUIPMENT | Schedule PM | PM done
PV | PV INSPECTION - D | 7
PV | WEATHER MONITORING STATION - D | 7
PV | ACRS ROBOTS OPERATION - D | 7
PVSS | DAILY SUBSTATION INSPECTION - D | 7
PVSS | POWER TRANSFORMER DGA TEST - D | 7
General | INDOOR HOUSEKEEPING - D | 7
PVSS | CCTV INSPECTION - D | 7
PVSS | WEATHER MONITORING STATION - W | 9
PVSS | SVG COOLING UNITS DUST CLEANING - W | 6
PVSS | EDG TEST RUN - SB-W | 1
PVSS | EDG TEST RUN - SS- W | 1
PV | POWER STATION MAINTENANCE - M | 1
PV | SUBSTATION PANELS CLEAINING - M | 33
PV | FIRE EXTINGHUSHER INSPECTION - M | All
PV | SECURITY SYSTEM INSPECTION - M | All
HSE | HSE PPE INSPECTION - M | 1
General | MAIN GATE,ROAD BLOCKERS MAINTENANCE - M | 1
PV | POWER STATION MAINTENANCE - HY | 14
PV | ARCS ROBOTS MAINTENANCE - HY | 131
PV | SCB'S MAINTENANCE - HY
| HVAC SYSTEM MAINTENANCE - M | 2
| TOTAL | 249
| COMPLIANCE SCORE | 0%
| PENDING | 100%
Week 3 (16 April To 22 April)
| EQUIPMENT | Schedule PM | PM done
PV | PV INSPECTION - D | 7
PV | WEATHER MONITORING STATION - D | 7
PV | ACRS ROBOTS OPERATION - D | 7
PVSS | DAILY SUBSTATION INSPECTION - D | 7
PVSS | POWER TRANSFORMER DGA TEST - D | 7
PVSS | INDOOR HOUSEKEEPING - D | 7
PVSS | CCTV INSPECTION - D | 7
PVSS | WEATHER MONITORING STATION - W | 1
PVSS | SVG COOLING UNITS DUST CLEANING - W | 6
PVSS | EDG TEST RUN - SB-W | 1
PVSS | EDG TEST RUN - SS- W | 1
PV | POWER STATION MAINTENANCE - M | 33
PV | HVAC SYSTEM MAINTENANCE - M | 2
PV | WATER PUMPING SYSTEM MAINTENANCE - M | 1
HSE | Emergency Response Kit Inspection (first aid kits, electrical rescue kit, walkie-talkies, etc) | 1
PVSS | PERIMETER FENCE MAINTENANCE - M | 1
PV | PERIMETER LIGHTING SYSTEM MAINTENANCE - M | 1
PV | POWER STATION MAINTENANCE - HY | 14
PV | ARCS ROBOTS MAINTENANCE - HY | 133
PV | SCB'S MAINTENANCE - HY | 14
| TOTAL | 258
| COMPLIANCE SCORE | 0%
| PENDING | 100%
Week 4 (23 April To 29 April)
| EQUIPMENT | Schedule PM | PM done
PV | PV INSPECTION - D | 7
PV | WEATHER MONITORING STATION - D | 7
PV | ACRS ROBOTS OPERATION - D | 7
PVSS | DAILY SUBSTATION INSPECTION - D | 7
PVSS | POWER TRANSFORMER DGA TEST - D | 7
PVSS | INDOOR HOUSEKEEPING - D | All
PVSS | CCTV INSPECTION - D | 7
PVSS | WEATHER MONITORING STATION - W | 1
PVSS | SVG COOLING UNITS DUST CLEANING - W | 6
PVSS | EDG TEST RUN - SB-W | 1
PVSS | EDG TEST RUN - SS- W | 1
PV | WEATHER MONITORING STATION - M | 9
PV | POWER STATION MAINTENANCE - M | 33
PVSS | BATTERY BANKS MAINTENANCE - M | 1
PVSS | HVAC SYSTEM MAINTENANCE - M | 2
PVSS | FIRE FIGHTNING SYSTEM INSPECTION - M | 1
PV | OUTDOOR HOUSEKEEPING - M | All
PV | ASPHALT ROAD CLEANING - M | All
PV | POWER STATION MAINTENANCE - HY | 14
PV | ARCS ROBOTS MAINTENANCE - HY | 129
PV | SCB'S MAINTENANCE - HY | 14